## Integration
DVC Pre Payment Enginee Replacement
Sl | Category |  |  |  | Responsible | Consulted/ Knowledge Transfer | Remarks
1 | Implementation
| Installation of PrePayment ( Prefer Kubernetes) |  |  |  | Pre Payment Partner | Cuculus | Prepayment Partner will provide the build guide to Cuculus System Engioneering Team
| Configuration of DC ( HA Mode) |  |  |  | Pre Payment Partner | Cuculus
| Cloud Infra |  |  |  | Cuculus | Pre Payment Partner | Sizing requirement to be shared by Prepayment Partner
| Prepayment Master Configuration |  |  |  | Pre Payment Partner | Cuculus
| Database migration |  |  |  | Cuculus | Pre Payment Partner
Tariff Management & Simulator
|  |  | Jharkand Domestic |  | Pre Payment Partner | Cuculus
|  |  | Jharkand Commercial |  | Cuculus | Pre Payment Partner
|  |  | West Bengal Domestic |  | Cuculus | Pre Payment Partner
|  |  | West Bengal Comemrcial |  | Pre Payment Partner | Cuculus
| Debit/Credit Note Reconcille for consumer |  |  |  | Pre Payment Partner | Cuculus
| Sample Testing |  |  |  | Cuculus | Pre Payment Partner
| Reports / Dashboards |  |  |  | Pre Payment Partner | Cuculus
2 | Integration |  | Source | Destination
| Consumer & Device : Master Data Sync | UC1 | ZONOS | PrePaid | Cuculus | Pre Payment Partner
| New Account creation | UC2 | ZONOS | PrePaid | Cuculus | Pre Payment Partner
| Profile Update based on Tariff Structure | UC3 | ZONOS | PrePaid | Cuculus | Pre Payment Partner
| Hierarchy & Relationship Management | UC4 | ZONOS | PrePaid | Cuculus | Pre Payment Partner
| Prepaid to Postpaid / Postpaid to Pre Paid | UC5
| Reconnect | UC6 | PrePaid | ZONOS | Cuculus | Pre Payment Partner
| Disconnect | UC7 | PrePaid | ZONOS | Cuculus | Pre Payment Partner
| Data Reconciliation & Audit | UC8 | Billing | ZONOS- PrePaid | Cuculus | Pre Payment Partner
| Recharge : Current Balance | UC9 | PrePayment | JioUrja | Cuculus | Pre Payment Partner
| Payment Transaction Details | UC10 | PrePayment | Bank Gateway | Cuculus | Pre Payment Partner
| Master Data Sync | UC11 | PrePayment | JioUrja | Cuculus | Pre Payment Partner
| Daily Charge breakdown | UC12 | PrePayment | JioUrja | Cuculus | Pre Payment Partner
| SMS Notification | UC13 | PrePayment | SMS Gateway | Cuculus | Pre Payment Partner
| Useage Visibility : Daily Profile | UC14 | PrePayment | JioUrja | Cuculus | Pre Payment Partner